## ReportsSchedule
Schedule of Course Reports and Transmittals | [7 empty] | type course# here
| 2000-01-01 | Day 1 of Course (enter YOUR date in B3)
| 2000-01-06 | Day 5 of Course (enter YOUR date in B4)
a | Schedule |  | Subject | BSA National Scouting U | National Wood Badge Coordinator | Territory Training Coordinator (TTC) | Participant's Council(s) | Staff Advisor
Pre-course
a | June 30, year prior |  | Request for authorization to hold a course. Use the latest national version. | Via TTC | Via TTC | To | Copy | Copy
| 1999-05-06 | -240 days | Course budget and camp use permits |  |  | Copy | To | Copy
| 1999-06-05 | -210 days | Staff roster for TTC review |  |  | To | Copy | Copy
| 1999-09-03 | -120 days | Application for medical insurance (if needed) |  |  |  | To | Copy
| 1999-10-03 | -90 days | Participant sign-up reports |  |  |  | To | Copy
| 1999-11-02 | -60 days | Participant sign-up reports |  |  |  | To | Copy
| 1999-11-17 | -45 days | Participant sign-up reports |  |  | To | Copy
| 1999-12-02 | -30 days | Sign-up report (participant roster confirming minimum of 30 signed up and paid in full) | To | Copy | To | Copy | Copy
Post-course
| 2000-02-05 | Within 30 days | Course director's closeout report including the following attachments: • Final staff roster • Final participant roster • Any uncertified participants* (names and circumstances) • Participants by Scouting position • Future staff recommendations (staff and participant) • Comments and recommendations | To | To | To | Copy | Copy
| 2000-02-05 | Within 30 days | World Friendship Fund donations transmittal | To BSA International Dept (Forn B-3) | Copy |  |  | Copy
| 2000-03-06 | Within 60 days | Financial Summary Report – a listing of major sources of revenue and expenses |  |  | To | Copy | Copy
| As tickets complete |  | Application for Training Recognition |  |  |  | To | Copy
| 2001-08-06 | 19 months | Final ticket report | Copy | Copy | To | Copy | Copy
*Uncertified participants are people who start on Day One but do not finish the course.
Important: It is the course director's responsibility to see that all reports concerning a Wood Badge course are filed electronically and on time, according to the Schedule of Course Reports and Transmittals. Signatures on all forms, reports and other documents relating to Wood Badge may be typed. Reports and other documents need to be sent as noted by the schedule to the Territory Training Coordinator, National Wood Badge Coordinator, and Scouting U.
National Wood Badge Coordinator's email is NationalWoodBadgeCoodinator@gmail.com Scouting U's email is NationalTraining.Course@scouting.org