## Sheet1
Presentor | Day | # |  | Backgnd | Rec'd 3/1 | Color Marker | Final Copy | Print Pages | Video | Ready
Gary | 1 | 1 |  | Complete | 2005-03-07 | Complete | Complete | Complete | n/a
Stuart | 1 | 3 | Video | Complete | 2005-02-11 | Complete | Complete | Complete
Randy Ticket | 1 | 3a |  | Complete | 2005-02-04 | Complete | Complete | Complete | n/a | Complete
Chuck | 2 | 1 |  | Complete | 2005-03-01 | Complete | Complete | Complete | n/a | Complete
Paul | 2 | 2 | Video | Complete | 2005-02-11 | Complete | Complete | Complete
Dickie/Jason | 2 | 4 | Video | Complete | 2005-03-02 | Complete | Complete | Complete
Dickie | 3 | 0 |  | Complete | 2005-03-02 | Complete | Complete | Complete | n/a | Complete
A.J. | 3 | 1 |  | Complete | 2005-02-11 | Complete | Complete | Complete | n/a | Complete
Tom | 3 | 3 |  | Complete | 2005-02-11 | Complete | Complete | Complete |  | Complete
Chris/Mark | 4 | 1 |  | Complete | 2005-02-25 | Complete | Complete | Complete | n/a | Complete
Craig/Kris | 4 | 2 |  | Complete | 2005-02-11 | Complete | Complete | Complete | n/a | Complete
John M/Richard | 4 | 3 |  | Complete | 2005-02-11 | Complete | Complete | Complete | n/a | Complete
Nancy/Mark | 5 | 1 |  | Complete | 2005-03-01 | Complete | Complete | Complete | n/a | Complete
James/Richard | 5 | 2 |  | Complete | 2005-02-27 | Complete | Complete | Complete | n/a | Complete
Randy | 6 | 1 | Video | Complete | 2005-03-06 | Complete | Complete | Complete
Gary | 6 | 2 | Video | Complete | 2005-03-07 | Complete | Complete | Complete
2005-03-07
2005-04-01
25 | Days to course